## raw
EPIC | ID | Title | User Story | Acceptance Criteria | Priority | Dependencies
Platform & Foundations | PLAT-01 | Baseline domain model & storage (Bronze/Silver/Gold) | As a platform engineer, I want a normalized schema and layered storage so runs are reproducible. | Bronze stores raw immutable files; Silver normalized; Gold reconciled outputs; all rows have source_id, run_id, rule_pack_version. Hashes prove immutability. | P0 | NONE
Platform & Foundations | PLAT-02 | Parser framework & mapping engine v1 | As an integrator, I can declaratively map PSP/bank files to our canonical schema. | UI JSON mapping; transforms (trim, regex, date parse, currency scale); versioned parsers; preview 100 rows; reject bucket file. | P0 | PLAT-01
Platform & Foundations | PLAT-03 | Rules/matching engine kernel | As a recon analyst, I can run deterministic and fuzzy rules in a pipeline. | Rule types: equality, composite, tolerance window; scoring; stop-at-first-match; rule hit metrics; idempotent by run_id. | P0 | PLAT-01
Platform & Foundations | PLAT-04 | Audit & evidence framework | As an auditor, I can export all inputs, rules, outputs used in a run. | One-click evidence pack zip per run; tamper-evident hash; action log for config changes. | P0 | PLAT-01
Platform & Foundations | PLAT-05 | RBAC & Auth (OIDC/SAML) | As an admin, I can manage roles and SSO. | Roles Admin/Analyst/Viewer; brand/country row-level guards; 2FA enforcement toggle; audit user actions. | P0 | NONE
Platform & Foundations | PLAT-06 | Scheduler & job orchestration | As an ops user, I can schedule daily imports & recons. | Cron UI; backoff; dead-letter for failing files; re-runs do not duplicate results. | P0 | PLAT-02, PLAT-03
Platform & Foundations | PLAT-09 | Observability | As an operator, I can see pipeline health and file throughput. | Per job metrics; per-file rows in/out/rejects; OpenTelemetry traces; dashboards. | P0 | PLAT-06
Data Integration & Mapping | INT-01 | Connectors: SFTP/HTTPS uploads | As an integrator, I can ingest files via SFTP/HTTPS. |  | P0 | PLAT-02
Data Integration & Mapping | INT-02 | CSV/XLSX/JSON ingestion v1 | As an integrator, I can ingest common flat files. | Header detection, delimiter selection, date/amount patterns, preview, schema validation. | P0 | PLAT-02
Data Integration & Mapping | INT-05 | Duplicate file detection | As an operator, I want to prevent duplicate ingest. | Checksum; refuse duplicate unless forced with note. | P0 | PLAT-02
Data Integration & Mapping | INT-06 | Mapping versioning & rollback | As an admin, I can version and rollback mappings. |  | P0 | PLAT-02
Data Integration & Mapping | INT-07 | Field dictionaries (status/method codes) | As a config manager, I can maintain dictionaries per PSP/version. |  | P0 | PLAT-02
Data Integration & Mapping | INT-08 | Data quality gates | As an operator, I can block bad files/rows. | Column count; type mismatches; negative-amount rule; configurable severity. | P0 | PLAT-02
Transaction Validation | VAL-01 | Deterministic ID match | As a recon analyst, I can match Internal.TransactionId to PSP.ExternalId. | Summary metrics and unmatched queues are generated. | P0 | INT-01..08, PLAT-03
Transaction Validation | VAL-02 | Composite key match | As a recon analyst, I can match using Amount+Currency+AuthCode+Time window. | PSP profiles choose strategy; metrics available. | P0 | VAL-01
Transaction Validation | VAL-03 | Time & amount tolerance rules | As a recon analyst, I can configure tolerances. |  | P0 | VAL-02
Transaction Validation | VAL-04 | Status canonicalization map | As a recon analyst, PSP statuses map to canonical statuses. |  | P0 | INT-07
Transaction Validation | VAL-05 | Duplicate detection | As a recon analyst, I can detect duplicate clusters. | Same key appears >1 in source; flagged as duplicates. | P0 | PLAT-03
Transaction Validation | VAL-07 | Run summaries & drill-through | As a team lead, I can see % matched, breaks by type, rule hit rates. | Export unmatched; drill-through to rows. | P0 | VAL-01..05
Fee Calculation | FEE-01 | Contract model v1 | As a finance admin, I can model PSP fees per method/brand/currency. | Fixed, %, hybrid; min/max; tiered by volume; effective dates; JSON DSL. | P0 | CFG-03, CFG-04
Fee Calculation | FEE-02 | Fee engine & rounding policies | As a finance user, I can compute expected fees accurately. | Configurable rounding; currency minor units; auditable results. | P0 | FEE-01
Fee Calculation | FEE-03 | Fee variance vs PSP statements | As an analyst, I can compare expected vs actual fees. | Threshold classification; exceptions pushed to cases. | P0 | FEE-02, INT-01..03
Net Settlement Calculation | SET-01 | Expected settlement ledger | As a finance user, I can compute expected net settlements. | Group by PSP/MID/Date/Currency; Gross, Refunds, Chargebacks, Fees, Reserves, FXAdj, NetExpected. | P0 | FEE-02, VAL-01..05
Settlement vs Bank Reconciliation | BREC-01 | Match expected settlements to bank entries | As a treasury analyst, I can match expected settlements to bank lines. | Reference+Amount+Date window; tolerance per account. | P0 | SET-01, INT-04
Settlement vs Bank Reconciliation | BREC-02 | Variance categorization | As an analyst, I can categorize variances. | Amount, date, currency, bank fee; push to cases. | P0 | BREC-01
Mismatch & Investigation | INV-01 | Case entity & queues | As an analyst, I can manage cases for exceptions. | Case types; links to rows; severity; SLA; assignee; watchers. | P0 | VAL-01..07, FEE-03, BREC-02
Mismatch & Investigation | INV-02 | Workflow: assign, comment, labels, attachments | As a team, we can collaborate on cases. |  | P0 | INV-01
Reporting & Analytics | REP-01 | Reconciliation dashboard | As a manager, I can view recon health and top root causes. | Auto-match %, breaks by PSP/method, run health, top root causes. | P0 | VAL-01..07, PLAT-09
User & Access Management | UAM-01 | Role definitions & permissions matrix | As an admin, I can define roles and permissions. |  | P0 | PLAT-05
User & Access Management | UAM-02 | Row-level security (brand/country) | As an admin, I can restrict data by brand/country. |  | P0 | PLAT-05, PLAT-01
User & Access Management | UAM-03 | SSO (OIDC/SAML) & 2FA | As a user, I log in via SSO with optional 2FA. |  | P0 | PLAT-05
User & Access Management | UAM-05 | Access & action logs (exportable) | As a security reviewer, I can export access and action logs. |  | P0 | PLAT-04, PLAT-05
PSP Config & Contract Mgmt | CFG-01 | PSP profiles (formats, tz, currencies, MIDs) | As a config manager, I can set PSP profiles. |  | P0 | PLAT-02
PSP Config & Contract Mgmt | CFG-02 | Status/method mapping dictionaries | As a config manager, I can set mappings per PSP and version. |  | P0 | PLAT-02
PSP Config & Contract Mgmt | CFG-03 | Contract store (fees, reserves, payout schedules) | As a finance admin, I can store contracts and schedules. |  | P0 | PLAT-01
PSP Config & Contract Mgmt | CFG-04 | Versioning & effective dating | As a finance admin, I can version contracts with effective dates. |  | P0 | CFG-03
Automation & Notifications | AUTO-01 | Pipelines end-to-end (importâ†’normalizeâ†’matchâ†’feeâ†’settlementâ†’bank rec) | As an ops user, I can run the full pipeline automatically. |  | P0 | PLAT-06, INT-01..08, VAL-01..07, FEE-01..03, SET-01, BREC-01..02
Automation & Notifications | AUTO-02 | Late file handling & re-runs | As an ops user, I can handle late files and safe re-runs. |  | P0 | PLAT-06
Non-Functional, Security & Ops | NFR-01 | Performance targets | As a sponsor, the platform meets volume and latency targets. | 10M rows/day; T+1 06:00 processing; p95 query <3s. | P0 | PLAT-01..03, PLAT-09
Non-Functional, Security & Ops | NFR-02 | Security controls | As a security officer, the platform enforces baseline security. | TLS 1.2+; at-rest encryption; secrets vault; least privilege. | P0 | PLAT-05
Platform & Foundations | PLAT-07 | Notifications (Email/Slack/Teams) | As an analyst, I receive alerts for failures and SLA breaches. | Channel templates; notify on run end, failures, SLA breach; deep links. | P1 | PLAT-06
Platform & Foundations | PLAT-08 | FX & time services | As a finance user, I want consistent FX rates and timestamps in UTC. | Central FX table; mid/buy/sell; effective timestamp; UTC canonicalization utilities. | P1 | PLAT-01
Platform & Foundations | PLAT-10 | Data retention & PII minimization | As a compliance officer, I can enforce retention and minimize PII. | Configurable retention per table; tokenization for sensitive fields; purge jobs logged. | P1 | PLAT-01
Data Integration & Mapping | INT-03 | API connector scaffold | As an integrator, I can pull from PSP/bank APIs. | OAuth2/API key; pagination; rate-limit handling; checkpointing cursors. | P1 | PLAT-02
Data Integration & Mapping | INT-04 | Bank formats MT940 / CAMT.053 / BAI2 | As an integrator, I can parse standard bank statement formats. |  | P1 | PLAT-02
Transaction Validation | VAL-08 | Replay a run with frozen inputs | As an auditor, I can replay a run deterministically. |  | P1 | PLAT-01, PLAT-04
Fee Calculation | FEE-04 | Component breakdown per transaction | As a finance user, I can see fee components per transaction. |  | P1 | FEE-02
Fee Calculation | FEE-05 | Approval workflow for fee changes | As a controller, I can approve/reject fee changes. | Draftâ†’Reviewâ†’Approve; audit who/when; past runs unaffected. | P1 | PLAT-04
Net Settlement Calculation | SET-02 | Partial & split settlements | As a finance user, I can support partial/split settlements. |  | P1 | SET-01
Net Settlement Calculation | SET-03 | Settlement calendars per PSP | As an analyst, I can model PSP payout calendars. |  | P1 | CFG-01
Net Settlement Calculation | SET-04 | Cash forecast view | As a treasury analyst, I can view expected cash by currency. | Daily expected cash; confidence band using historical variance. | P1 | SET-01
Settlement vs Bank Reconciliation | BREC-03 | Partial/combined bank hits | As an analyst, I can reconcile partial or combined payouts. |  | P1 | BREC-01
Settlement vs Bank Reconciliation | BREC-04 | Aging & SLA tracking for unsettled | As a team lead, I can see aging of unreconciled payouts with SLAs. |  | P1 | BREC-02
Mismatch & Investigation | INV-03 | Auto-close on resolution events | As an analyst, cases auto-close when resolution occurs. |  | P1 | INV-01
Mismatch & Investigation | INV-05 | Root cause codes & reporting | As a lead, I can tag root causes and report on them. |  | P1 | INV-01
Mismatch & Investigation | INV-06 | Roll-forward of unmatched items | As an analyst, unmatched items roll forward to future cycles. |  | P1 | INV-01
Mismatch & Investigation | INV-07 | Evidence snapshot for case | As an auditor, I can export case evidence. |  | P1 | INV-01, PLAT-04
Reporting & Analytics | REP-02 | Fee impact & variance report | As a finance user, I can analyze fees and variances. |  | P1 | FEE-03
Reporting & Analytics | REP-03 | Cash positions & forecast | As a treasury analyst, I can see cash positions and forecasts. |  | P1 | SET-04
Reporting & Analytics | REP-04 | Aged breaks & SLA | As a lead, I can view aged breaks and SLA performance. |  | P1 | INV-01..06
Reporting & Analytics | REP-05 | Self-serve filtered reports + drill | As a user, I can filter and drill into details. |  | P1 | PLAT-09
Reporting & Analytics | REP-06 | Exports CSV/XLSX & scheduled pushes | As a user, I can export or schedule report deliveries. |  | P1 | PLAT-06
User & Access Management | UAM-04 | API keys & rotation | As an admin, I can provision and rotate API keys. |  | P1 | PLAT-05
PSP Config & Contract Mgmt | CFG-05 | Change approvals & audit | As a controller, I can approve contract changes with audit. |  | P1 | PLAT-04
Automation & Notifications | AUTO-03 | Notification rules & templates | As an admin, I can configure notification rules and templates. |  | P1 | PLAT-07
Non-Functional, Security & Ops | NFR-03 | Compliance (GDPR/SOC2 readiness) | As a compliance officer, I can evidence controls. |  | P1 | PLAT-04, NFR-02
Non-Functional, Security & Ops | NFR-04 | Backups/restore & DR plan | As an operator, I can restore data and fail over. |  | P1 | PLAT-01
Transaction Validation | VAL-06 | Heuristic/fuzzy suggestions | As an analyst, I get suggested probable matches to review. | Score threshold; analyst acceptance creates link. | P2 | VAL-03
Fee Calculation | FEE-06 | Rolling reserve schedule support | As a finance user, I can model rolling reserves. |  | P2 | FEE-01
Fee Calculation | FEE-07 | FX markup & scheme fees | As a finance user, I can model FX markups and scheme fees. |  | P2 | FEE-01, PLAT-08
Settlement vs Bank Reconciliation | BREC-05 | GL export/journal suggestions | As an accountant, I can export journals to GL. |  | P2 | BREC-02
Mismatch & Investigation | INV-04 | Bulk actions (merge/split/close) | As an analyst, I can bulk manage cases. |  | P2 | INV-01
Reporting & Analytics | REP-07 | BI connectors (Power BI/Tableau) | As a data team, we can connect external BI tools. |  | P2 | PLAT-09
Automation & Notifications | AUTO-04 | Webhooks for events | As a developer, I can subscribe to system events via webhooks. |  | P2 | PLAT-06
Non-Functional, Security & Ops | NFR-05 | Data residency options | As an admin, I can choose regional data residency. |  | P2 | PLAT-01
Non-Functional, Security & Ops | NFR-06 | Cost observability (per run/file) | As a sponsor, I can see cost per run/file/PSP. |  | P2 | PLAT-09
Net Settlement Calculation | SET-05 | Scenario recalculation (what-if) | As a finance lead, I can run what-if scenarios without overwriting originals. |  | P3 | SET-01, FEE-02
Field Mappings |  |  | Should notify when a profile is not complete
Field Mappings |  |  | Create a way to add all the fields in a table like manner
Field Mappings |  |  | The listing should group the mappings by target field, simmilarly to the way the Target Field dropdown works on the Creation page

## Technical
ID | Description | Status | Prio
1 | If the ImportSilverCsvCommand fails, remove the file uploaded by the ImportBronzeCsvCommand | DONE | High
2 | All logs should be pushed to the DB | Pending | Medium
3 | Logs pushed to the DB should be automatically cleared after X days | Pending | Medium
4 | raw_payments should be enriched with start_date and end_date for the first and last row in the payload | DONE | Medium
5 | gold.reconciliation_comments should store the ruleId | Pending | High
6 | Cases get created automatically when a settlement fails | Pending | High
7 | Move the Settlement to a RabbitQueue based solution | Pending | Medium
8 | Move the FileUpload to a RabbitQueue based solutioni | Pending | Medium
9 | auth0/keycloack? | Pending | Medium
10 | db backups to coldstorage nightly | Pending | Medium
11 | Notify SuperAdmins when the application stops | Pending | Medium
12 | Healthcheck page | Pending | Medium
13 | Job to clear the Serilogs table | Pending | Medium
14 | Returned errors should have a correlationId to link it to the logs | Pending | High
15 | All Apps should log into a single sync | Pending | High
16 | Run names should have DATE-Time format | Pending | Low
17 | Add Partial Matches | Pending | High
18 | Add the in the layout /css/fa-solid.css | Pending | Low

## Deployment
Start the UI, the producer and then the consumer

## Enterprise Features
Imonas V4 Backlog (Build Areas 1–4)
Generated 2026-02-04 ¦ Status defaults to Backlog.
Epic ID | Epic | Feature ID | Feature | Story ID | Story Title | Description | Acceptance Criteria | Dependencies | Priority | Build Area | Status
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.1 | Settlement data model + ingestion | S1.1.1 | Create core tables for settlement legs | Add silver.settlement_transactions (raw normalized rows); add gold.settlement_legs (canonical legs); add settlement_batches and settlement_batch_items. | Can store settlement ref, batch id, value date, currency, gross/net, fee, source account, PSP id, file id, row hash; Idempotent inserts (no duplicate ingests). |  | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.1 | Settlement data model + ingestion | S1.1.2 | Settlement file parser pipeline | Add SettlementFile type; parser supports CSV with header mapping (reuse Field Mappings). | Upload settlement file → processed → visible in Files; rows appear in Settlement Transactions grid; invalid rows go to quarantine with row-level errors. | S1.1.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.2 | Canonical “Legs” and lifecycle modeling | S1.2.1 | Introduce canonical transaction-leg schema | Define canonical leg types: CAPTURE, REFUND, CHARGEBACK, PAYOUT, FEE, REVERSAL. Support multiple legs per internal payment and mapping from settlement rows. | One internal payment may produce multiple canonical legs; settlement rows can map to PAYOUT and FEE legs. | S1.1.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.2 | Canonical “Legs” and lifecycle modeling | S1.2.2 | Status and lifecycle mapping for settlement | Add canonical settlement statuses: EXPECTED, RECEIVED, PARTIAL, FAILED; extend Status Mappings UI for settlement sources. | Status mapping UI supports settlement-specific statuses per bank/PSP source; canonical settlement status visible on settlement legs. | S1.2.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.3 | Matching engine extensions: many-to-many / netting | S1.3.1 | Support match groups | Add gold.match_groups and gold.match_group_items; allow internal/PSP/settlement items in same group; compute totals and deltas. | A match group can contain 1:1, 1:many, many:1, many:many; group totals/deltas calculated and displayed. | S1.2.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.3 | Matching engine extensions: many-to-many / netting | S1.3.2 | Netting/aggregation match strategy | Add matching strategy AGGREGATE_SUM to match N captures to 1 payout (and fees) within tolerance using configured rule. | Given payout Net=9700, system can match captures Gross=10000 and fees=300 (or equivalent) per rule; output includes computed breakdown. | S1.3.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.3 | Matching engine extensions: many-to-many / netting | S1.3.3 | Time-window matching for settlement lag | Extend rule execution to include T+0..T+N matching windows for settlement delay. | Transactions can match settlement within configured window (e.g., 0–3 days) without manual intervention. | S1.3.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.4 | UX: 3-way run results | S1.4.1 | Add “Settlement Coverage” metrics to run | Extend run metrics to show internal↔PSP, PSP↔settlement, and full 3-way coverage; bucket unmatched by source. | Run shows % internal matched to PSP, % PSP matched to settlement, % fully 3-way matched, and unmatched counts by source. | S1.1.2; S1.3.1 | 1 | 1) 3-way + netting | Backlog
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | F1.4 | UX: 3-way run results | S1.4.2 | Exception creation from missing leg | Add variance types: MISSING_PSP, MISSING_SETTLEMENT, PARTIAL_SETTLEMENT; enable one-click case creation from unmatched legs. | Create case from unmatched leg; case auto-links related candidates (same reference/amount window) and records missing-leg variance type. | S1.4.1 | 1 | 1) 3-way + netting | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.1 | Rule versioning + effective dating | S2.1.1 | Add versioning model | Add tables rules and rule_versions with version, effective_from/to, status, created_by. Make prior versions immutable. | Editing a rule creates a new version; previous versions remain immutable; reconciliation run records exact rule version set used. |  | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.1 | Rule versioning + effective dating | S2.1.2 | Rule set snapshot per run | Persist a rule_set_id per run containing list of active rule versions used for that run. | Re-run can reproduce identical results even if rules changed later; UI shows rule set id and versions. | S2.1.1 | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.2 | Explainability (match trace) | S2.2.1 | Store match evidence | Add gold.match_evidence: rule id/version, fields compared, computed values, similarity score, tolerance/window used. | Every matched item has a 'Why matched?' panel showing rule name+version, evaluated conditions pass/fail, final score/tolerances/window. | S2.1.2 | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.2 | Explainability (match trace) | S2.2.2 | Deterministic match ordering | Define explicit tie-breakers (priority, confidence score, stable sorting) to eliminate nondeterministic outcomes. | Same inputs + same rule set → identical match groups every run; tie-break criteria visible in config/docs. | S2.2.1 | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.3 | Backtesting / simulation | S2.3.1 | Add “Simulation Run” type | Introduce simulation runs that persist results separately and do not finalize matches. | Can pick date range + PSP + candidate rule versions and run simulation; results stored and viewable without affecting production runs. | S2.1.2 | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.3 | Backtesting / simulation | S2.3.2 | Compare baseline vs candidate | Diff view comparing baseline run to simulation: match uplift, exception reduction, changed matches. | UI shows matched %, unmatched count, variance totals side-by-side; list of changed matches with evidence. | S2.3.1; S2.2.1 | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-2 | Rule Versioning + Explainability + Backtesting | F2.3 | Backtesting / simulation | S2.3.3 | Promote rule version | Add action to promote candidate version to active (ties into approvals). | Promotion requires approval; activated version becomes effective-dated; audit record created. | S2.3.2; S4.1.1 | 2 | 2) Rules: versioning/explain/sim | Backlog
EPIC-3 | Automation Connectors + Idempotent Ingestion | F3.1 | SFTP connector | S3.1.1 | Connection model + secrets handling | Create SFTP connection entity (host/port/user/auth). Store secrets in secure store abstraction (KeyVault-ready). Add connection test UI. | No secrets stored in plaintext DB; connection test validates access and lists remote directory contents. |  | 3 | 3) Connectors + ingestion hardening | Backlog
EPIC-3 | Automation Connectors + Idempotent Ingestion | F3.1 | SFTP connector | S3.1.2 | Scheduled pull → File record creation | Scheduler fetches new remote files, creates Files entries, triggers processing. Add fingerprinting to avoid duplicates. | Automated pulls ingest new files; duplicate remote files are not reprocessed; processing status visible in Files. | S3.1.1 | 3 | 3) Connectors + ingestion hardening | Backlog
EPIC-3 | Automation Connectors + Idempotent Ingestion | F3.2 | HTTP/API pull connector | S3.2.1 | Generic API connector framework | Build API connector framework supporting API key/OAuth, pagination, and date-range pulls. | Can configure endpoint template and pull daily statements; failures retry with backoff; results land as Files/rows like CSV uploads. |  | 3 | 3) Connectors + ingestion hardening | Backlog
EPIC-3 | Automation Connectors + Idempotent Ingestion | F3.3 | Cloud storage connector (S3/Azure Blob) | S3.3.1 | Add storage connector abstraction | Support polling a bucket/container prefix and ingesting new objects into Files pipeline. | Can poll configured prefix on schedule; new objects ingest once; metadata recorded (etag/version) for idempotency. |  | 3 | 3) Connectors + ingestion hardening | Backlog
EPIC-3 | Automation Connectors + Idempotent Ingestion | F3.4 | Ingestion hardening | S3.4.1 | Row-level idempotency and replay | Compute row hash per row+source+PSP+file; enforce uniqueness; add replay/backfill option into new run without corrupting history. | Re-upload same file does not duplicate rows; replay supports forced reprocess into new run with full traceability. | S3.1.2 | 3 | 3) Connectors + ingestion hardening | Backlog
EPIC-3 | Automation Connectors + Idempotent Ingestion | F3.4 | Ingestion hardening | S3.4.2 | Quarantine workflow | Store invalid rows with reasons; allow fixing mappings and reprocessing quarantined rows. | Invalid rows visible in quarantine with row-level reasons; admin can remediate mapping and reprocess successfully. | S3.4.1 | 3 | 3) Connectors + ingestion hardening | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.1 | Maker–checker approval flows | S4.1.1 | Approval workflow engine | Implement approval workflow for Rules, Mappings, Fee Contracts, Manual Matches, Case Closure, Write-offs. | Any change creates Pending Approval record; only authorized approvers can accept/reject with comment; approvals are audited. |  | 4 | 4) Controls + audit | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.1 | Maker–checker approval flows | S4.1.2 | Approvals UI | Build approvals queue with filters and diff view (before/after), plus impact preview where available. | Approver sees exact diff and can approve/reject; approved changes apply atomically; rejected changes remain inactive. | S4.1.1 | 4 | 4) Controls + audit | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.2 | Immutable audit trail | S4.2.1 | Append-only audit log | Create audit_events with actor, action, entity, entity_id, timestamp, correlation id, payload hash. | Audit records cannot be edited/deleted via app; every critical action emits an audit event; events include correlation id. |  | 4 | 4) Controls + audit | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.2 | Immutable audit trail | S4.2.2 | Audit viewer | Create searchable audit viewer with filters and export. | Search by user/entity/date range; export audit events to CSV; pagination and RBAC enforced. | S4.2.1 | 4 | 4) Controls + audit | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.3 | Evidence packs for cases and matches | S4.3.1 | Attachments + notes | Enable attachments and threaded notes for cases and match groups; record author and timestamp. | Case stores and displays attachments and notes with author+timestamp; attachment downloads audited. |  | 4 | 4) Controls + audit | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.3 | Evidence packs for cases and matches | S4.3.2 | Export evidence pack | One-click export creates ZIP with case summary, linked transactions, match evidence, and attachments. | ZIP contains case summary JSON/CSV; linked internal/PSP/settlement transactions; match evidence; all attachments. | S4.3.1; S2.2.1 | 4 | 4) Controls + audit | Backlog
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | F4.4 | Segregation of duties guardrails | S4.4.1 | Prevent self-approval | Enforce SoD: users cannot approve their own changes; enforce via role rules and approval engine. | System prevents self-approval; violation attempt logged; enforced for all approval-requiring entity types. | S4.1.1 | 4 | 4) Controls + audit | Backlog

## Enterprise Features Summary
Imonas V4 Backlog Summary
Epic ID | Epic | Story Count | Build Area
EPIC-1 | 3-Way Reconciliation + Netting (Internal ↔ PSP ↔ Bank/Settlement) | 9 | 1) 3-way + netting
EPIC-2 | Rule Versioning + Explainability + Backtesting | 7 | 2) Rules: versioning/explain/sim
EPIC-3 | Automation Connectors + Idempotent Ingestion | 6 | 3) Connectors + ingestion hardening
EPIC-4 | Controls: Maker-Checker + Approvals + Immutable Audit + Evidence Packs | 7 | 4) Controls + audit